## Summary
BLUE CORAL - Quotation for Digital Transformation & Unified Platform
American Chamber of Commerce in Vietnam (AmCham Vietnam) - RFP AmCham-RFP-2026-WEB
Client: | AmCham Vietnam (HCMC + Hanoi Chapters)
Vendor: | Blue Coral (Powered by ADNS CO., LTD) - https://bluecoral.vn
Address: | 8/7D Phan Huy Ich St., Tan Son Ward, Ho Chi Minh City, Vietnam
Prepared by: | Ms. Uyen Tran
Approved by: | Mr. Nguyen - 0979 477 101
Quotation date: | 15 May 2026
Submission deadline: | 26 May 2026
Quote validity: | 90 days from issue date
Currency: | VND (primary) / USD (reference, FX rate 26,250 VND/USD)
Implementation duration: | 4 months - two parallel workstreams (Website & AMS)
Warranty: | 12 months from go-live (final 10% released after warranty period)
PROPOSED ARCHITECTURE - WordPress + Custom Microservices
Presentation layer (WordPress) | WordPress 6.x (latest LTS) - public website, CMS, content authoring, role-based editorial workflows. Custom theme built on a performance-optimized base (Astra/GeneratePress). Gutenberg blocks for AmCham brand components. The tech stack is similar to websites such as https://www.nasa.gov and https://www.whitehouse.gov.
AMS data layer (Laravel) | Laravel Framework- owns membership, events, finance, and audit data. Same PHP runtime as WordPress, deployed on the same infrastructure but isolated as a separate application with its own database. WordPress consumes the Laravel API via authenticated REST calls (Laravel Sanctum tokens).
Unified PHP stack - no over-engineering | • One language (PHP), one runtime (PHP-FPM), one database engine (MariaDB). • No Node.js, no Postgres, no separate microservice runtime - keeps ops/maintenance lean. • WordPress and Laravel share infra but have separate codebases and separate databases for clean boundaries. • AmCham team and any future vendor only need PHP/Laravel skills to maintain the AMS.
Why this architecture | • AmCham retains 100% ownership of AMS source code (Laravel) and database (MariaDB). • WordPress is replaceable/upgradable without touching the AMS data layer. • Laravel isolates sensitive data (PDPA compliance) from the public WordPress attack surface. • Lower long-term licensing cost vs. ChamberMaster / Glue Up SaaS (no per-member fees).
Integration approach | Laravel Sanctum-authenticated REST APIs between WordPress and the Laravel AMS. Laravel Queues (Redis-backed) for asynchronous flows (renewal triggers, email dispatch, e-invoice issuance). Stripe / VNPay / Momo for payments. QuickBooks Online API for finance sync. Viettel/Misa for Vietnam e-invoicing.
Compliance | PDPA (Decree 13/2023/NĐ-CP) by design: consent capture, audit log of data access, data export & deletion APIs. GDPR-aligned for EU members. SSL/TLS everywhere, WAF, daily encrypted backups.
Data ownership | All source code (WordPress theme + Laravel app), MariaDB databases, design assets, and cloud account credentials are transferred to AmCham after milestone M2. No vendor lock-in.
COST SUMMARY - YEAR 1
Item | Sheet reference | Price (VND) | Price (USD) | Notes
A. Website & CMS - Implementation (one-time) | A. Website & CMS | 350550000 | 13354.29 | Design, dev, member portal, SEO, training
B. AMS - Implementation (one-time) | B. AMS | 481650000 | 18348.57 | Membership, events, email, finance, compliance
Hosting & Cloud - Year 1 (12 months) | Hosting & Cloud | 136686000 | 5207.09 | App, DB, staging, CDN, monitoring, SSL
Managed Services & Support - Year 1 (12 months) | Managed Services | 176700000 | 6731.43 | 30 hours/month + SLA + event standby
Third-party Licenses - Year 1 (12 months, pass-through) | Third-party Licenses | 54120000 | 2061.71 | Email service, e-invoice, monitoring, consent
B. AMS - Data Migration (OPTIONAL, not in base total) | B. AMS | 73150000 | 2786.67 | ChamberMaster + Constant Contact data migration - quoted separately
TOTAL YEAR 1 (VAT included) |  | 1199706000 | 45703.09 | Includes: one-time implementation + Year-1 hosting + Year-1 managed + Year-1 licenses
of which: One-time implementation (A + B) |  | 832200000 | 31702.86 | Paid across 7 milestones - see Payment & Warranty sheet
of which: Recurring Year-1 (Hosting + Managed + Licenses) |  | 367506000 | 14000.23 | Paid annually; Year 2+ at same unit price or upstream vendor adjustment
* VAT: design/dev/maintenance items 0% (VAT-exempt); Cloud Services 10%; Third-party Licenses pass-through. 5% discount applied to all sheets except Third-party Licenses.
* Optional Enhancements (separate sheet) are NOT included in the Year-1 total.
* Payment gateway transaction fees (Stripe/VNPay/Momo) and QuickBooks subscription are paid by AmCham directly.

## A. Website & CMS
BLUE CORAL - A. Website & CMS
BLUE CORAL Powered by ADNS CO., LTD |  | 8/7D Phan Huy Ich St., Tan Son Ward, Ho Chi Minh City, Vietnam |  |  |  |  | Project: | AmCham VN - Website & CMS (WordPress)
Prepared by: | Ms. Uyen Tran | [5 empty] | Duration: | Week 1 → Week 10 (~2.5 months)
Approved by: | Mr. Nguyen
Contact: | 0979 477 101
SCHEDULE | TASK | ESTIMATION (HOURS) |  |  |  |  | PRICE (VND) | PRICE (USD) | QTY | NOTES
|  | BA | DESIGN | DEV | PM | TOTAL
▸ Discovery & Analysis
Discovery & Analysis | Discovery - 2 chapters (HCMC + Hanoi) | 24 |  |  | 8 | 32 | 16000000 | 609.52 | 1 | Stakeholder interviews, audit of ChamberMaster + Constant Contact
| Information Architecture & Sitemap (unified) | 16 |  |  | 4 | 20 | 10000000 | 380.95 | 1 | URL strategy, taxonomy, EN+VI language plan
| Content audit & migration strategy | 16 |  |  | 4 | 20 | 10000000 | 380.95 | 1 | Classify content: migrate vs rewrite vs archive
▸ UI/UX Design
UI/UX Design | Design system & Gutenberg block library |  | 16 |  | 2 | 18 | 9000000 | 342.86 | 1 | Tokens, components, brand-locked, mobile-first
| Homepage (unified branding, 2 chapters) |  | 16 |  | 2 | 18 | 9000000 | 342.86 | 1 | Hero, news, events, sponsor, join CTA
| Member portal dashboard |  | 16 |  | 2 | 18 | 9000000 | 342.86 | 1 | Profile, renewal, invoice, events
| Events listing & detail page |  | 12 |  | 2 | 14 | 7000000 | 266.67 | 1 | Filter by chapter, calendar view
| Member / Company directory |  | 8 |  | 2 | 10 | 5000000 | 190.48 | 1 | Searchable, gated for members
| Sponsor & advertising pages |  | 8 |  | 2 | 10 | 5000000 | 190.48 | 1 | Profile, ad inventory, RFP form
| News / Insights template |  | 8 |  | 2 | 10 | 5000000 | 190.48 | 1 | Article, category, author
| Static & legal pages |  | 8 |  | 2 | 10 | 5000000 | 190.48 | 1 | Policy, Terms, Contact, 404, search
| Mobile responsive variants |  | 16 |  | 2 | 18 | 9000000 | 342.86 | 1 | All key flows across breakpoints
▸ Frontend Development
Frontend Development | WordPress theme customization |  |  | 40 | 8 | 48 | 24000000 | 914.29 | 1 | Child theme, hooks, customizer
| Custom Gutenberg blocks for AmCham components |  |  | 32 | 4 | 36 | 18000000 | 685.71 | 1 | Reusable, editor-friendly
| Mobile responsive implementation |  |  | 16 | 4 | 20 | 10000000 | 380.95 | 1 | Lighthouse mobile ≥ 90
| Performance optimization (< 3s load) |  |  | 16 | 2 | 18 | 9000000 | 342.86 | 1 | Image opt, CDN, lazy load, critical CSS
| Accessibility (WCAG 2.1 AA) |  |  | 12 | 2 | 14 | 7000000 | 266.67 | 1 | Audit + fix
▸ CMS & Backend Foundation
CMS & Backend Foundation | WordPress install + multisite config | 4 |  | 16 | 4 | 24 | 12000000 | 457.14 | 1 | EN + VI ready
| Database schema (WP ↔ Laravel bridge tables) | 4 |  | 24 | 4 | 32 | 16000000 | 609.52 | 1 | Link tables, ID mapping, sync state
| Role-based permissions (multi-team) | 4 |  | 24 | 4 | 32 | 16000000 | 609.52 | 1 | Admin, Editor, Membership, Events, Finance
| Media library + S3-compatible offload |  |  | 16 | 4 | 20 | 10000000 | 380.95 | 1 | Off-load uploads, CDN delivery
| SEO-friendly architecture |  |  | 16 | 4 | 20 | 10000000 | 380.95 | 1 | URL strategy, sitemap, schema.org, RankMath
| REST API client for Laravel AMS | 4 |  | 32 | 4 | 40 | 20000000 | 761.9 | 1 | WordPress consumer with Sanctum token handling
| Webhook & queue integration | 4 |  | 24 | 4 | 32 | 16000000 | 609.52 | 1 | Async events between WP and Laravel (Redis queue)
| WordPress security hardening |  |  | 16 | 4 | 20 | 10000000 | 380.95 | 1 | WAF rules, 2FA admin, login lockout, audit
▸ Self-service Member Portal
Self-service Member Portal | Authentication (WP + Laravel Sanctum tokens) |  |  | 20 | 2 | 22 | 11000000 | 419.05 | 1 | Email/OTP, Google SSO ready
| Profile management UI |  |  | 20 | 2 | 22 | 11000000 | 419.05 | 1 | Member edits profile & company info
| Renewal request flow (frontend) |  |  | 16 | 2 | 18 | 9000000 | 342.86 | 1 | Triggers AMS workflow + payment
| Invoice & receipt download |  |  | 12 | 2 | 14 | 7000000 | 266.67 | 1 | PDF download, history
| Event registration UI |  |  | 20 | 2 | 22 | 11000000 | 419.05 | 1 | Self-register, group booking entry
▸ Sponsor & Advertising Module
Sponsor & Advertising Module | Sponsor profile management (CPT + tier display) |  | 4 | 16 | 2 | 22 | 11000000 | 419.05 | 1 | Logo, description, tier
| Searchable advertising opportunities |  |  | 24 | 2 | 26 | 13000000 | 495.24 | 1 | Ad inventory, pricing, request form
▸ Deployment, QA & Handover
Deployment, QA & Handover | QC & UAT testing | 8 |  |  | 4 | 12 | 6000000 | 228.57 | 1 | Test plan, regression
| Deploy to production (staging → prod) |  |  | 8 | 2 | 10 | 5000000 | 190.48 | 1 | Blue-green deployment
| Training for AmCham staff |  |  |  | 8 | 8 | 4000000 | 152.38 | 1 | 1 session: editor + admin
| Documentation (User guide) | - | - | - | - | - | Free of charge | Free | 1 | Provided at no cost - EN + VI
| Go-live & 1-week hypercare |  |  | 4 | 4 | 8 | 4000000 | 152.38 | 1 | Standby support post-launch
Subtotal (before discount, before VAT) | [6 empty] | 369000000 | 14057.14
Discount (5%) | [6 empty] | -18450000 | -702.86
After discount | [6 empty] | 350550000 | 13354.29
VAT (0%) - design / dev / maintenance VAT-exempt | [6 empty] | 0 | 0
TOTAL | [6 empty] | 350550000 | 13354.29
* Monthly fees for third-party services (Email, e-invoice, etc.) are NOT included - see 'Third-party Licenses' sheet.
* Reference FX rate: 26,250 VND/USD. Contract & invoicing in VND.

## B. AMS
BLUE CORAL - B. AMS
BLUE CORAL Powered by ADNS CO., LTD |  | 8/7D Phan Huy Ich St., Tan Son Ward, Ho Chi Minh City, Vietnam |  |  |  |  | Project: | AmCham VN - AMS (Laravel)
Prepared by: | Ms. Uyen Tran | [5 empty] | Duration: | Week 1 → Week 16 (~4 months)
Approved by: | Mr. Nguyen
Contact: | 0979 477 101
SCHEDULE | TASK | ESTIMATION (HOURS) |  |  |  |  | PRICE (VND) | PRICE (USD) | QTY | NOTES
|  | BA | DESIGN | DEV | PM | TOTAL
▸ Discovery & Analysis (AMS)
Discovery & Analysis (AMS) | AMS requirements & process mapping (2 chapters) | 24 |  |  | 8 | 32 | 16000000 | 609.52 | 1 | Membership lifecycle, event ops, billing
| Data model design (unified MariaDB schema) | 16 |  | 8 | 4 | 28 | 14000000 | 533.33 | 1 | Member, Company, Interaction, Transaction - Laravel Eloquent
| Laravel API & WordPress integration architecture | 16 |  | 8 | 2 | 26 | 13000000 | 495.24 | 1 | Sanctum auth, REST contract, queue flows
| Migration plan from CM + Constant Contact | 12 |  |  | 4 | 16 | 8000000 | 304.76 | 1 | Strategy & gap analysis (execution optional)
▸ Database & Core Platform
Database & Core Platform (Laravel AMS) | Laravel application scaffold (Laravel 11) | 4 |  | 40 | 8 | 52 | 26000000 | 990.48 | 1 | App skeleton, Sanctum auth, base REST APIs
| MariaDB schema (Eloquent migrations & seeders) | 4 |  | 16 | 4 | 24 | 12000000 | 457.14 | 1 | Indices, foreign keys, seed data
| Multi-chapter data isolation |  |  | 16 | 2 | 18 | 9000000 | 342.86 | 1 | Per-chapter scope via Eloquent global scopes; roll-up reports
| Interaction history & audit logs |  |  | 16 | 2 | 18 | 9000000 | 342.86 | 1 | PDPA: track who viewed/edited PII (Laravel Auditing)
| Laravel API + Sanctum auth (consumed by WordPress) | 4 |  | 20 | 4 | 28 | 14000000 | 533.33 | 1 | Secured WP ↔ Laravel calls; Laravel Queues for async
▸ Membership Management
Membership Management | Member & company profile module | 4 |  | 24 | 4 | 32 | 16000000 | 609.52 | 1 | CRUD, custom fields, attachments
| Automated onboarding workflow | 4 |  | 20 | 4 | 28 | 14000000 | 533.33 | 1 | Welcome sequence, document collection
| Automated renewal workflow | 4 |  | 20 | 4 | 28 | 14000000 | 533.33 | 1 | Reminders, invoicing, payment, status
| Member directory + advanced search |  |  | 12 | 2 | 14 | 7000000 | 266.67 | 1 | Filters: industry, chapter, tier
▸ Event Management
Event Management | Event creation & calendar (admin) | 4 | 8 | 24 | 4 | 40 | 20000000 | 761.9 | 1 | Recurring, capacity, ticket types
| Online registration + payment | 4 | 8 | 24 | 4 | 40 | 20000000 | 761.9 | 1 | Member vs non-member pricing
| Group & table bookings | 4 | 8 | 24 | 4 | 40 | 20000000 | 761.9 | 1 | Tables of 10, seat assignment
| QR-code ticketing |  | 4 | 16 | 2 | 22 | 11000000 | 419.05 | 1 | Auto-generate QR, email delivery
| Mobile check-in interface | 4 | 8 | 24 | 4 | 40 | 20000000 | 761.9 | 1 | Staff scan-in app
| Attendance tracking & reports |  |  | 16 | 2 | 18 | 9000000 | 342.86 | 1 | Per-member history, export
▸ Communications & Email (Constant Contact replacement)
Communications & Email (Constant Contact replacement) | Transactional email |  |  | 10 | 2 | 12 | 6000000 | 228.57 | 1 | Receipts, notifications via SES driver
| Bulk email engine | 4 |  | 12 | 2 | 18 | 9000000 | 342.86 | 1 | Newsletter, segmentation, throttled sending
| Email template builder + brand lock |  | 4 | 12 | 2 | 18 | 9000000 | 342.86 | 1 | Blade templates, locked components
| Campaign automation workflows | 4 |  | 12 | 2 | 18 | 9000000 | 342.86 | 1 | Drip, behavior triggers (Laravel Scheduler + Queue)
▸ Financial Integration
Financial Integration | QuickBooks Online API integration (2-way) | 8 |  | 32 | 8 | 48 | 24000000 | 914.29 | 1 | Sync invoices, payments, customers
| Invoice generation & PDF templates | 4 | 4 | 16 | 4 | 28 | 14000000 | 533.33 | 1 | VAT-compliant, EN/VI
| Payment gateway (Stripe + VNPay/Momo) | 4 |  | 24 | 4 | 32 | 16000000 | 609.52 | 1 | Card, bank transfer
| Vietnam e-invoice integration (Viettel/Misa) | 12 |  | 24 | 8 | 44 | 22000000 | 838.1 | 1 | Decree 123/2020 compliance
| Reconciliation & financial reports |  |  | 12 | 2 | 14 | 7000000 | 266.67 | 1 | Aging, revenue by chapter/event
| Renewal billing automation | 4 |  | 16 | 4 | 24 | 12000000 | 457.14 | 1 | Auto-invoice on renewal cycle
▸ Compliance & Security
Compliance & Security | PDPA (Decree 13/2023) compliance | 16 |  | 24 | 4 | 44 | 22000000 | 838.1 | 1 | Consent records, DSR, breach notify
| GDPR alignment (EU members) | 8 |  | 16 | 2 | 26 | 13000000 | 495.24 | 1 | RTBF, DPA template
| Data export & deletion APIs |  |  | 16 | 2 | 18 | 9000000 | 342.86 | 1 | Member self-service data export
| Security hardening + 3rd-party pen-test |  |  | 20 | 2 | 22 | 11000000 | 419.05 | 1 | OWASP top 10, audit before go-live
▸ Deployment, QA & Handover
Deployment, QA & Handover | QC & UAT testing | 16 |  |  | 12 | 28 | 14000000 | 533.33 | 1 | Full regression, AmCham UAT sign-off
| Performance & load testing |  |  | 16 | 4 | 20 | 10000000 | 380.95 | 1 | Simulate event-day spike
| Deploy to production |  |  | 12 | 4 | 16 | 8000000 | 304.76 | 1 | Cut-over plan
| Training (admin + finance + member rep) |  |  |  | 24 | 24 | 12000000 | 457.14 | 1 | 1 combined session
| Documentation (User guide) | - | - | - | - | - | Free of charge | Free | 1 | Provided at no cost - EN + VI
| Go-live & 2-week hypercare | 4 |  | 8 | 4 | 16 | 8000000 | 304.76 | 1 | Standby support
▸ Data Migration (OPTIONAL - quoted separately, NOT in base total)
Data Migration (OPTIONAL) | ChamberMaster export & data mapping | 12 |  | 40 | 8 | 60 | 30000000 | 1142.86 | 1 | Member, company, interaction history
| Constant Contact subscriber migration | 4 |  | 16 | 2 | 22 | 11000000 | 419.05 | 1 | Lists, segments, suppression
| Historical event & transaction data | 8 |  | 24 | 4 | 36 | 18000000 | 685.71 | 1 | Past 3-5 years (scope TBD)
| Data cleansing & validation | 16 |  | 16 | 4 | 36 | 18000000 | 685.71 | 1 | Dedupe, normalize, manual review
Subtotal (before discount, before VAT) | [6 empty] | 507000000 | 19314.29
Discount (5%) | [6 empty] | -25350000 | -965.71
After discount | [6 empty] | 481650000 | 18348.57
VAT (0%) - design / dev / maintenance VAT-exempt | [6 empty] | 0 | 0
TOTAL | [6 empty] | 481650000 | 18348.57
OPTIONAL ADD-ON (priced separately, NOT included in base total above)
Optional subtotal (before discount, before VAT) | [6 empty] | 77000000 | 2933.33
Discount (5%) | [6 empty] | -3850000 | -146.67
VAT (0%) - design / dev / maintenance VAT-exempt | [6 empty] | 0 | 0
OPTIONAL TOTAL | [6 empty] | 73150000 | 2786.67
* Monthly fees for third-party services (Email, e-invoice, etc.) are NOT included - see 'Third-party Licenses' sheet.
* Reference FX rate: 26,250 VND/USD. Contract & invoicing in VND.

## Hosting & Cloud
BLUE CORAL - Cloud Hosting & Infrastructure (Year 1)
BLUE CORAL Powered by ADNS CO., LTD |  | 8/7D Phan Huy Ich St., Tan Son Ward, Ho Chi Minh City, Vietnam |  | Project: | AmCham VN - Hosting Y1
Prepared by: | Ms. Uyen Tran |  |  | Duration: | 12 months from go-live
Approved by: | Mr. Nguyen - 0979 477 101
SCHEDULE | TASK | DESCRIPTION | PRICE (VND) | PRICE (USD) | QTY | NOTES
▸ Cloud Infrastructure (Year 1)
Cloud Services | PHP Application Server (WordPress + Laravel AMS) | Single production server hosting both apps on PHP-FPM with separate virtual hosts • CPU 6 cores / RAM 24 GB / SSD 200 GB • Region: Singapore (low latency to VN) • Daily backup, 30-day retention | 43200000 | 1645.71 | 12 months | Consolidated PHP stack - no separate Node server
Cloud Services | Managed MariaDB (WordPress + AMS databases) | Managed MariaDB instance hosting both WP and Laravel databases (separate DBs, shared engine) • 4 vCPU / 16 GB RAM / 200 GB SSD • Point-in-time recovery • Read replica for reporting | 36000000 | 1371.43 | 12 months | One DB engine for the whole stack
Cloud Services | Redis (queue + cache) | Managed Redis for Laravel Queues, sessions, and WordPress object cache • 1 vCPU / 4 GB RAM | 7200000 | 274.29 | 12 months
Cloud Services | Staging & Dev environment | Lower-spec staging for UAT & dev branch (WP + Laravel) | 14400000 | 548.57 | 12 months
Cloud Services | Object storage (media + backup) | S3-compatible, 500 GB initial + auto-scale Media files, uploads, archive backups | 12000000 | 457.14 | 12 months
Cloud Services | CDN & DDoS protection | Cloudflare Pro tier • Global CDN, image optimization • WAF, DDoS L3/L4/L7 • 99.9% uptime SLA | 7200000 | 274.29 | 12 months
Cloud Services | SSL Certificates (wildcard) | Wildcard SSL for amchamvietnam.com + subdomains (member., admin., api.) | 0 | 0 | 12 months | Complimentary, value 3,600,000 VND
Cloud Services | Email deliverability infrastructure | Dedicated IP + DKIM/SPF/DMARC setup for domain reputation (Email sending volume fees NOT included - see Third-party Licenses) | 6000000 | 228.57 | 12 months
Cloud Services | Monitoring & alerting | Uptime Robot Pro + Sentry error tracking + custom dashboards Alerts via email + Slack 24/7 | 4800000 | 182.86 | 12 months
Subtotal (before discount, before VAT) |  |  | 130800000 | 4982.86
Discount (5%) |  |  | -6540000 | -249.14
After discount |  |  | 124260000 | 4733.71
VAT (10%) |  |  | 12426000 | 473.37
TOTAL (VAT included) |  |  | 136686000 | 5207.09
* Uptime commitment ≥ 99.5% (RFP requirement).
* Year 2 onward: same unit price; may adjust ≤ 10%/year per infra inflation.
* AmCham Vietnam retains 100% data ownership; full backup export available anytime.
* VAT 10% applied (Cloud Services standard rate).

## Managed Services
BLUE CORAL - Managed Services & Operations (Year 1)
BLUE CORAL Powered by ADNS CO., LTD |  | 8/7D Phan Huy Ich St., Tan Son Ward, Ho Chi Minh City, Vietnam |  | Project: | AmCham VN - Managed Services Y1
Prepared by: | Ms. Uyen Tran |  |  | Duration: | 12 months from go-live
Approved by: | Mr. Nguyen - 0979 477 101
SCHEDULE | TASK | DESCRIPTION | PRICE (VND) | PRICE (USD) | QTY | NOTES
▸ Maintenance & Technical Support (Year 1)
Managed Services | Standard Support Plan - 30 hours/month | Scope: • 24/7 hosting & monitoring administration • Daily backup + scheduled disaster recovery tests • Periodic security & threat scans • Performance tuning & SEO health checks • Production hot-fixes (no extra fee during warranty) • Operations support (module config, permission tuning, big event ops) • Minimum 30 minutes counted per task | 180000000 | 6857.14 | 12 months | 3 months complimentary after go-live (value ~45,000,000 VND)
▸ Response SLA (per RFP Section 4)
Support Tier | Critical (P1) - site/AMS down, payment failures | • Response: ≤ 30 min (24/7) • Recovery target: ≤ 4 hours • Channel: hotline + email + dedicated Slack | Included | - | - | Included in Standard plan
Support Tier | High (P2) - important feature broken | • Response: ≤ 2h business hours, ≤ 4h after hours • Recovery target: ≤ 1 business day | Included | - | - | Included in Standard plan
Support Tier | Medium (P3) - minor bug, not blocking | • Response: ≤ 4h business hours • Recovery target: ≤ 3 business days | Included | - | - | Included in Standard plan
Support Tier | Low (P4) - question or small request | • Response: ≤ 1 business day • Recovery target: ≤ 5 business days | Included | - | - | Included in Standard plan
▸ Major Event Support
Event Support | Standby engineer for major events | On-site/remote standby for events >300 attendees (Charity Ball, Mid-Autumn Gala, etc.) • 1 engineer 4h before + throughout the event • 4 standbys/year included | 0 | 0 | 4 sessions/year | Complimentary, value ~24,000,000 VND
Event Support | Additional standby (beyond 4) | Per-session pricing for standbys beyond the included 4 | 6000000 | 228.57 | Per session | Charged when used
Subtotal (before discount, before VAT) |  |  | 186000000 | 7085.71
Discount (5%) |  |  | -9300000 | -354.29
After discount |  |  | 176700000 | 6731.43
VAT (0%) - design / dev / maintenance VAT-exempt |  |  | 0 | 0
TOTAL |  |  | 176700000 | 6731.43
* Maintenance services VAT-exempt (per VN tax classification for design / dev / maintenance services).
* During the 12-month warranty: all bugs related to implementation scope are fixed at no charge.
* New feature development outside scope: separate Change Request quote.
* Upgrade to Premium (60 hours/month) available as needs grow.

## Third-party Licenses
BLUE CORAL - Third-party License & SaaS Fees (Year 1)
BLUE CORAL Powered by ADNS CO., LTD |  | 8/7D Phan Huy Ich St., Tan Son Ward, Ho Chi Minh City, Vietnam |  | Project: | AmCham VN - Third-party Y1
Prepared by: | Ms. Uyen Tran |  |  | Duration: | 12 months
Approved by: | Mr. Nguyen - 0979 477 101
SCHEDULE | TASK | DESCRIPTION | PRICE (VND) | PRICE (USD) | QTY | NOTES
▸ Third-party License & SaaS Fees (Year 1)
Email Service | Bulk email service (replaces Constant Contact) | Amazon SES Production or SendGrid Pro • Estimated 500,000 emails/month = 6M/year • Dedicated IP + advanced analytics • ~70% cost saving vs Constant Contact | 28080000 | 1069.71 | 12 months | ~$90/month - billed by actual volume
Email Service | Transactional email (notifications, receipts) | Same SES/SendGrid account - no separate fee | 0 | 0 | 12 months | Included in the bulk plan above
E-invoice | Vietnam e-invoice service (Viettel/Misa/VNPT) | Electronic invoices per Decree 123/2020/NĐ-CP • ~5,000 invoices/year plan • API integration with AMS | 12000000 | 457.14 | 12 months | Recommended: Viettel Sinvoice
Payment Gateway | Stripe (international payments) | No setup fee; transaction fee 3.4% + $0.30/txn Transaction fees billed by actual volume - not included in this quote | 0 | 0 | Pay-per-use | Charged at the gateway
Payment Gateway | VNPay / Momo (local payments) | No setup fee; transaction fee 1.5–2.2% Transaction fees billed by actual volume | 0 | 0 | Pay-per-use | Charged at the gateway
Finance Integration | QuickBooks Online subscription | AmCham retains existing QuickBooks subscription - Blue Coral does not markup Reference: ~$90–200/month depending on plan (paid directly by AmCham) | 0 | 0 | Paid by AmCham | Already in place
Communication | Slack workspace (bonus) | Free tier sufficient for team comms & alert routing | 0 | 0 | Free | Setup at no cost
Monitoring | Sentry error tracking | Team plan - error monitoring for both WordPress and microservice | 7800000 | 297.14 | 12 months | ~$26/month × 12
Monitoring | Uptime Robot Pro | Included in Hosting sheet | 0 | 0 | - | See Hosting
Security | SSL wildcard (in Hosting) | Reference only | 0 | 0 | - | See Hosting
PDPA Compliance | Consent management platform (optional) | Cookie + PDPA consent log (CookieYes Pro or equivalent) | 6240000 | 237.71 | 12 months | ~$20/month
Subtotal (before discount, before VAT) |  |  | 54120000 | 2061.71
TOTAL |  |  | 54120000 | 2061.71
* All licenses are pass-through cost; Blue Coral does not add a markup. AmCham may pay vendors directly.
* Payment gateway transaction fees (Stripe/VNPay/Momo) charged at gateway based on actual volume - not in this quote.
* Year 2 onward: unit prices unchanged or per upstream vendor adjustment.

## Optional Enhancements
BLUE CORAL - Optional Enhancements (Phase 2 & 3)
BLUE CORAL Powered by ADNS CO., LTD |  | 8/7D Phan Huy Ich St., Tan Son Ward, Ho Chi Minh City, Vietnam |  | Project: | AmCham VN - Optional
Prepared by: | Ms. Uyen Tran |  |  | Duration: | Post go-live
Approved by: | Mr. Nguyen - 0979 477 101
SCHEDULE | TASK | DESCRIPTION | PRICE (VND) | PRICE (USD) | QTY | NOTES
▸ Mobile App (Phase 2) - React Native (cross-platform)
Mobile | AmCham Member App - React Native (iOS + Android, single codebase) | Member portal app: profile, events, networking directory, QR check-in • React Native - single codebase for iOS + Android • ~40% cost saving vs two native apps • Faster release cadence and lower long-term maintenance | 360000000 | 13714.29 | One-time | Phase 2 (~4 months)
▸ AI & Automation Add-ons
AI | AI member recommendation engine | Suggests events and member-to-member networking matches based on industry, interest, attendance history | 120000000 | 4571.43 | One-time | High ROI for engagement
AI | AI chatbot for member support | FAQ, renewal guidance, event registration - trained on AmCham knowledge base | 85000000 | 3238.1 | One-time | Reduces email support load by 40–60%
AI | Auto-generated event recap & news draft | AI drafts event recap and news posts from photos + bullet points | 45000000 | 1714.29 | One-time
▸ Advanced Reporting & BI
BI | Executive dashboard (member health, revenue, engagement) | Real-time dashboard for Board & ED Member churn, LTV, event ROI, sponsor activation | 95000000 | 3619.05 | One-time
BI | Advanced financial reporting suite | Profit by chapter / event / sponsor tier; budget vs actual | 65000000 | 2476.19 | One-time
▸ Enhanced Member Experience
Member UX | Member-to-member messaging & networking | Internal messaging, business card exchange, intro request workflow | 85000000 | 3238.1 | One-time
Member UX | Member badges & gamification | Tier badge, event attendance streak, contribution points | 45000000 | 1714.29 | One-time
Member UX | Job board for member companies | Member companies post jobs, members apply, AmCham does not operate | 85000000 | 3238.1 | One-time
▸ Extended Integrations
Integration | Salesforce / HubSpot CRM bridge | For high-tier sponsors who need lead data auto-routed to their CRM | 65000000 | 2476.19 | One-time
Integration | Zoom / Teams event integration | Auto-create virtual events, auto-sync attendance | 35000000 | 1333.33 | One-time
Integration | Government PDPA reporting API | Once MIC releases official PDPA reporting API | 45000000 | 1714.29 | One-time | Per regulatory roadmap
Subtotal (before discount, before VAT) |  |  | 1130000000 | 43047.62
VAT (0%) - design / dev / maintenance VAT-exempt |  |  | 0 | 0
TOTAL |  |  | 1130000000 | 43047.62
* All optional features - NOT included in the base implementation price (Sheets A + B).
* AmCham may select features individually or bundle for 5–10% discount.
* Optional quotes valid for 12 months from go-live.
* Design / dev / maintenance VAT-exempt.

## Payment & Warranty
BLUE CORAL - Payment Schedule & Warranty
Applies to one-time implementation (Sheets A + B, excluding optional Data Migration)
Milestone | Description | % of total | Amount (VND) | Release condition
M1 | Kick-off & Discovery | 30% | 249660000 | Upon contract signing + AmCham provides credentials for existing systems (ChamberMaster, Constant Contact)
M2 | Combined: UI/UX approval + AMS core demo (member DB + onboarding + renewal) | 20% | 166440000 | AmCham sign-off on design system + key pages; AMS core UAT pass
M3 | Website CMS go-live | 10% | 83220000 | Website CMS production go-live, OR 20 days from UAT demo date - whichever comes first
M4 | AMS modules complete + integration | 30% | 249660000 | Events, finance/QuickBooks, e-invoice, email modules complete; full WordPress ↔ Laravel integration; UAT sign-off
M5 | Full platform go-live | 10% | 83220000 | Production cut-over complete (Website + AMS); system stable for 14 days
TOTAL (Implementation A + B - VAT-exempt) |  | 100% | 832200000
WARRANTY TERMS
Warranty period | 12 months from full platform go-live (M5)
Scope of warranty | • Free fix of all bugs related to implementation scope (Sheets A + B) • Critical hot-fix 24/7 • Includes 30 hours/month of Managed Services (see Managed Services sheet)
Out of scope | • New features beyond scope (handled via Change Request) • Defects caused by AmCham or third parties accessing the system outside Blue Coral • Third-party outages (QuickBooks API down, Stripe outage, etc.)
Warranty SLA | • Critical (P1): response ≤ 30 min, recovery ≤ 4h (24/7) • High (P2): response ≤ 2h business hours • Medium/Low: per standard SLA (see Managed Services sheet)
Payment retention | Payment follows the milestone schedule above (M1–M5). No additional retention beyond the M5 final 10%.
Extended warranty (optional) | After 12 months, AmCham may renew Managed Services for the next 12 months at Year-1 unit price
GENERAL TERMS
Currency | VND (primary). USD shown for reference at FX rate 26,250 VND/USD. Contract & invoicing in VND.
VAT | • Design / development / maintenance services (Sheets A, B, Managed Services, Optional): VAT-exempt (0%) • Cloud Services (Sheet Hosting & Cloud): VAT 10% • Third-party Licenses: pass-through, vendor charges VAT directly
Quote validity | 90 days from 15 May 2026
Payment method | Bank transfer. E-VAT invoice issued per milestone.
Ownership | AmCham Vietnam owns 100% of source code, data, design assets, and infrastructure accounts after M1 + M2 are paid.
Confidentiality | NDA signed alongside the contract. Compliant with PDPA Decree 13/2023/NĐ-CP and GDPR.