## The Myst - Sapa v1
BLUE CORAL Powered by ADNS | [6 empty] | Project: | The Myst Sapa Resort
8/7D Phan Huy Ich, Ward 15, Tan Binh District, Ho Chi Minh City | [6 empty] | Duration: | 3 Months
Prepared by: | Ms. Uyen Tran
Approved by: | Mr. Nguyen
Number | 0979 477 101
SCHEDULE | TASK | ESTIMATION (HOURS) |  |  |  |  | PRICE (vnd) | PRICE (USD) | QUANTITY | NOTES
|  | BA | DESIGN | DEV | PM | TOTAL
UI/UX Design | Business Analytics |  |  |  |  | — | — | —
| Homepage | 8 | 40 | 32 | 4 | 84 | 37514400 | 1617 | 1
| Discover Sapa & Details |  | 24 | 24 | 2 | 50 | 22330000 | 962.5 | 1
| Award Page |  |  | 4 | 2 | 6 | 2679600 | 115.5 | 1
| Blog |  | 12 | 32 | 2 | 46 | 20543600 | 885.5 | 1
| Article Details |  | 12 | 8 | 1 | 21 | 9378600 | 404.25 | 1
| Events | 2 | 24 | 32 | 2 | 60 | 26796000 | 1155 | 1 | Banquet
| Events Details |  | 8 | 12 |  | 20 | 8932000 | 385 | 1
| Accommodation | 8 | 36 | 10 | 2 | 56 | 25009600 | 1078 | 1
| Business & Leisure |  | 32 | 10 | 2 | 44 | 19650400 | 847 | 1
| Dining |  | 8 | 10 | 2 | 20 | 8932000 | 385 | 1
| Facilities |  | 8 | 10 | 2 | 20 | 8932000 | 385 | 1
| MICE & Event |  | 8 | 18 | 2 | 28 | 12504800 | 539 | 1
| Gallery |  | 12 | 24 | 2 | 38 | 16970800 | 731.5 | 1
| Contact us | 2 | 8 | 4 | 2 | 16 | 7145600 | 308 | 1
| FAQs | 2 | 8 | 4 | 2 | 16 | 7145600 | 308 | 1
| Search |  | 8 | 20 | 1 | 29 | 12951400 | 558.25 | 1
| Information pages (Policy, Terms, etc) |  | 4 | 2 | 1 | 7 | — | — | One-time | Mostly text, minimum design like: Legal, Terms, etc.
Setup & Configs | Design Database Structure | 8 |  | 8 | 2 | 18 | 8038800 | 346.5 | 1
| Content and Media | 1 |  |  | 1 | 2 | — | — | One-time
| Manage User Roles & Permissions | 8 |  |  | 2 | 10 | — | — | 1
Setup workflow | Monitor & Redirections |  |  | 24 | 4 | 28 | 12504800 | 539 | 1 | Month
Third-Party software Integration | Integration of any 3rd party's system (based on Javascript) | 1 |  | 2 | 1 | 4 | — | — | One-time | Per system Ex: https://www.appsflyer.com/
Modules | Cookie consent |  |  | 20 | 2 | 22 | 9825200 | 423.5 | 1
| Forms | 2 |  | 8 |  | 10 | 4466000 | 192.5 | 1
| Video block |  | 0.5 | 4 |  | 4.5 | 2009700 | 86.625 | 1 | Portrait Layout in Mobile
| Generate data cho LLM (Optional) | 12 |  | 40 | 12 | 64 | 28582400 | 1232 | 1
| Display & Video 360 | 8 |  | 40 | 8 | 56 | 25009600 | 1078 | 1 | Excludes filming and photography.
Deployment | ConfigServer Security & Firewall: • Injection • Broken Authentication • Security Misconfiguration • Cross Site Scripting • Insufficient Logging & Monitoring | 2 |  | 5 | 1 | 8 | — | — | One-time
| Deploy |  |  | 8 |  | 8 | — | — | One-time
| QC Testing | 4 |  | 5 | 2 | 11 | 4912600 | 211.75 | 1
Launch website
Total | [6 empty] | 342765500 | 14774.375
Offer (15%) | [6 empty] | 51414825 | 2216.1562
Total (VAT included): | [6 empty] | 291350675 | 12558.2188
Reviewed by Vũ kiều Linh Approved by Vũ Hồng Nam
* Monthly fee for these tools not included

## Quotation - Phase 1 (hidden)
ADNS INC., LTD |  | Project: | Talentnet Project
8/7D Phan Huy Ich, Ward 15, Tan Binh District, Ho Chi Minh City |  | Duration: | 2.5 → 3 Months
Approved by: | Mr. Nguyen
Contact: | 0979 477 101
SCHEDULE | TASK | PRICE (vnd) | QUANTITY | NOTES
Business Analytic | Copywriting for Website Guideline | Free of charge | one-time | Estimate: • Collect infomations and analyze ( 01 Weeks )
Solutions Consulting
UI/UX Design | Mockups and UI/UX Design for: - Homepage - About Us - Our Services - Services details - Insights & Expertise - Expertise detail - Experts - Experts detail - News - News detail - Contact Us - Search - 404 - Information pages (Policy, Terms, etc) | 84835000 | 26 pages
Front-end & Back-end Development | Convert design to static pages | 58750000
| Back-end development for management modules: - Content and Media Management - Multilanguage - Dynamic Content - Lead Form - Email Automation - Manage User Roles - SEO Optimization - Avanced Search - Chatbox - Detailed tracking & analysis | 82250000 | based on designs
Deployment | ConfigServer Security & Firewall: - Injection - Broken Authentication - Security Misconfiguration - Cross Site Scripting - Insufficient Logging & Monitoring | Free of charge
| Implement and deploy: - Deploy and QA Testing. - Launch website | Free of charge
Support and Maintenance | - Server backup periodically - Support website/server recovery when problems occur - Remote help in handling the website during operation | 0 |  | Offer 03 months free, valued at 14,940,000 ₫
Total (not TAX included) |  | 225835000
VAT (0%) |  | 0
Grand total |  | 225835000

## Server & Managed Services (Mini (hidden)
ADNS INC., LTD |  | Project: | Goka Project
8/7D Phan Huy Ich, Ward 15, Tan Binh District, Ho Chi Minh City |  | Duration: | 3 → 3.5 Months
Approved by: | Mr. Nguyen
Contact: | 0979 477 101
TASK |  | PRICE (vnd) | QUANTITY | DESCRIPTION
Cloud Services | eCommerce Hosting | 22320000 | 12 Months | CPU 6 cores RAM 8 Gb SSD 100 Gb Daily backup
| SSL Certificates | 0 | 12 Months | Value at 135,000₫
| WAF Application | 0 | 12 Months | Value at 5,580,000 đ
Managed Services | 12 hours of website technical support a month. Technical Support scope of work* - Managed hosting - SSL Secured - Daily Backups - Minimum 30 Minutes counted per Task received - Security & Threat Scans - Performance Monitoring - SEO Monitoring & Tweaks (Onpage) - Priority support - Website consulting Other support during the term of contract (module configs, provide solutions, etc.) |  | 12 Months | Offer 03 months free, valued at 14,940,000 ₫
Deployment |  | Free of charge
Total (not TAX included) |  | 22320000
Offer (12.5%) |  | 2790000 | (before Tax)
VAT (10%) |  | 1953000
Grand total |  | 21483000
* Monthly fee for these tools not inluded

## Modules (hidden)
ADNS INC., LTD |  | Project: | Goka Project
8/7D Phan Huy Ich, Ward 15, Tan Binh District, Ho Chi Minh City |  | Duration: | 2 → 3.5 Months
Approved by: | Mr. Nguyen
Contact: | 0979 477 101
SCHEDULE | TASK | PRICE (vnd) | QUANTITY | NOTES
Business Analytic | Copywriting for Website Guideline | Free of charge | one-time | Estimate: • Collect infomations and analyze ( 01 Weeks )
Solutions Consulting
Other Modules | One Step Checkout (Ex: topzone.vn) | 22325000 |  | Based on Vue / React
| Stock Locations | 17625000 |  | Track whether or not a product is available at stores
| Installment Payment | 15275000 |  | https://payon.vn
| Shipping Cost | N/A |  | Only needed when deploying One Step Checkout. Cost depends on module complexity.
Deployment | Implement and deploy: - Deploy and QA Testing. - Launch website | Free of charge
Total (not TAX included) |  | 55225000
Offer (5%) |  | 2761250
Grand total |  | 52463750
* Monthly fee for these tools not inluded