## 1. Cover
BLUE CORAL
Powered by ADNS · Enterprise web & digital experience studio
PROPOSAL & QUOTATION
SAM Tuyen Lam Website Consolidation Programme
One master brand · three properties · three languages · three booking flows
PREPARED FOR SAM Tuyen Lam Hospitality Group |  |  | REFERENCE BC-2026-0526-SAM · Issued 26 May 2026 · Valid until 25 June 2026
PROGRAMME INVESTMENT AT A GLANCE
PHASE 1 — DESIGN & BUILD |  | PHASE 2 — HOSTING & SUPPORT (Y1) |  | TOTAL PROGRAMME — Year 1
841891050 |  | 66000000 |  | 907891050
32380.425 |  | 12 months · VAT included |  | 34918.8865
ENGAGEMENT CONTEXT
Client | SAM Tuyen Lam Hospitality Group — Golf Course, Swiss-Belresort, Villa
Primary Domain | samtuyenlam.com.vn (consolidation of 4 legacy domains)
Reference Style | Hoiana.com (multi-property architecture) × NamiaRiverRetreat.com (emotional, healing tone)
Languages | Vietnamese · English · Korean
Booking Flows | Golf → VNPay · Swiss-Belresort → Hotel Link → Smile PMS · Villa → Lead capture
Engagement | Strategy, Design, Build, Migrate, Launch + 12-month Managed Services
Delivery | 20 weeks (5 months) from kickoff to launch · 4-week post-launch hypercare
CONTACT & APPROVALS
Prepared by | Ms. Uyen Tran — Account Director, Blue Coral
Approved by | Mr. Nguyen — Managing Director, ADNS |  |  | nguyen@bluecoral.vn · +84 979 477 101
Client sponsor | Mr. / Ms. ________________ (SAM Tuyen Lam) |  |  | Date of signature: ____ / ____ / 2026
This proposal is commercially confidential. Pricing and scope herein are valid for 30 days from the issue date.

## 2. Executive Summary
BLUE CORAL ▍ Powered by ADNS · 8/7D Phan Huy Ich, Tan Binh, Ho Chi Minh City · +84 979 477 101 · hello@bluecoral.vn
Executive Summary
01 · ENGAGEMENT OVERVIEW
SAM Tuyen Lam currently operates four disconnected websites — one per property and one legacy 360° VR portal. Each runs on different infrastructure, lacks a unified brand voice, and presents fragmented booking journeys to a global audience. This programme consolidates the four sites into a single master experience at samtuyenlam.com.vn, modelled on Hoiana's multi-property architecture and Namia River Retreat's emotional, healing tone. The new platform will deliver an Alpine-retreat narrative across three properties, three languages (VI / EN / KO), and three independent booking flows — with the marketing team in full control of campaigns through a permission-managed CMS.
02 · STRATEGIC OBJECTIVES
BRAND CONSOLIDATION |  |  | CONVERSION LIFT |  |  | INTERNATIONAL REACH
Unify 4 fragmented sites under one master brand narrative — Alpine retreat, healing, enduring love. |  |  | Persistent property-aware "Book" CTAs, friction-free booking journeys, direct-booking incentives. |  |  | Trilingual VI/EN/KO with Swiss-Belresort identity surfaced for inbound EN/KO traffic.
MARKETING AUTONOMY |  |  | PERFORMANCE & TRUST
Role-based CMS lets Marketing publish offers, blog, news, banners, pop-ups without engineering tickets. |  |  | Core Web Vitals green, WCAG-AA accessibility, hardened security (post-incident posture), full backup & DR.
03 · SCOPE AT A GLANCE — PROPERTY MAP
Property | Domain Path | Booking System |  | Primary Audience |  | Templates Delivered
SAM Tuyen Lam Golf Course | /samtuyenlamgolf | VNPay (booking → PMS) |  | Golfers · Couples |  | 1 Overview + 18-Hole + Coaching + Club House + Gallery + Booking
Swiss-Belresort Tuyen Lam | /swiss-belresorttuyenlam | Hotel Link → Smile PMS |  | 4★+ International · Wellness · MICE |  | 1 Property + 7 Room Types + Spa + MICE + Dining + Gallery + Booking
SAM Tuyen Lam Villa | /samtuyenlamvilla | Lead capture (temporarily closed) |  | Future launch · Newsletter audience |  | 1 Teaser + 5 Room Type design templates (no booking dev)
04 · PROGRAMME INVESTMENT
# | Phase | Description |  |  |  | Investment (VND) | Investment (USD)
1 | Design & Build | Discovery · IA · Visual Design · 14 page templates · Booking integrations · CMS · Multi-language · SEO · QA · Launch · 4-week hypercare |  |  |  | 841891050 | 32380.425
2 | Hosting & Support | Year 1 — Enterprise hosting · CDN · SSL · WAF · 20 hrs/month managed services |  |  |  | 66000000 | —
TOTAL PROGRAMME — Year 1 (VAT included) | [5 empty] | 907891050 | 34918.8865
05 · DELIVERY ROADMAP
Milestone | Phase |  |  | Duration | Key Deliverables
M0 | Discovery & Foundation |  |  | Weeks 1-2 | Sitemap signoff · Content audit · Brand narrative outline
M1 | Design |  |  | Weeks 3-8 | Design system + 14 visual templates approved
M2 | Build |  |  | Weeks 9-14 | Front-end · Back-end · CMS · Multi-language operational
M3 | Integration |  |  | Weeks 15-18 | VNPay · Hotel Link/Smile · 360° · Live chat · Analytics live
M4 | QA, UAT & Launch |  |  | Weeks 19-20 | 301 redirects · Security · Go-live · 4-week hypercare
M5+ | Hosting & Managed Services |  |  | 12 Months | SLA-backed support · backups · monitoring · monthly reports

## 3. Scope of Work
BLUE CORAL ▍ Powered by ADNS · 8/7D Phan Huy Ich, Tan Binh, Ho Chi Minh City · +84 979 477 101 · hello@bluecoral.vn
Scope of Work — Detailed Deliverables
The scope below is organised by workstream. Each line is a discrete deliverable with a defined acceptance output. All items are included in the Phase 1 investment unless explicitly marked optional.
# | Deliverable | Description | Acceptance Output
A · DISCOVERY & BRAND FOUNDATION
A.1 | Stakeholder workshops & content audit | On-site discovery with property GMs, marketing, IT, revenue. Inventory and quality-grade all assets across 4 legacy domains. | Discovery report + asset inventory
A.2 | Information architecture & sitemap | Master sitemap for 1 brand × 3 properties × 3 languages. URL strategy (clean, property-scoped, hreflang-ready). | Approved sitemap + URL map
A.3 | Brand narrative & content strategy | Brand storyline anchored on "Lost in nature, founding you" — nature, stillness, healing, enduring love. Tone guidelines, voice rules, lexicon. | Brand narrative doc + tone guide
A.4 | Design system & component library | Typography, colour, photographic mood, iconography, UI components (cards, hero, navigation, forms, modals). | Figma design system file
B · PAGE TEMPLATES — BRAND HOME
B.1 | Brand Home (master) | Sticky header · Full-screen hero video · Brand narrative block · 3 property gateways · 3 experience pillars · Featured offers grid · Audience-segment quick links · Gallery teaser · Blog & newsletter · Footer. | Responsive template — VI/EN/KO
C · PAGE TEMPLATES — GOLF PROPERTY
C.1 | Golf overview & sub-pages | 6 blocks: Hero · Course intro · 18-hole / Coaching / Club House · Golf-lifestyle experiences · Gallery + 360° · Final CTA. Club House nested children (Restaurant · Rooms · Pro Shop). | Responsive template + 3 sub-pages
D · PAGE TEMPLATES — SWISS-BELRESORT
D.1 | Resort overview | 7 blocks: Hero + Swiss-Bel identity · 151-room intro · Room grid · Spa & Wellness · Dining · MICE · Experiences · Gallery + 360° · Final CTA. | Responsive template
D.2 | Room Type pages (×3) | Deluxe Mountain View · Deluxe Golf View · Studio Mountain View · Family Deluxe Mountain View · King Suite Mountain View · Royal Suite Mountain View · Standard. | 3 detail templates with 360°
D.3 | Spa & Wellness | Curated wellness journeys, not service list. | Sub-page
D.4 | Dining | Restaurant & bar storytelling, menu module. | Sub-page
D.5 | MICE & Events | Venue specs, capacity tables, RFP form. | Sub-page + lead form
E · PAGE TEMPLATES — VILLA
E.1 | Villa teaser (Coming Soon) | Brand storytelling, "Love Trekk-in / Forest Service Hub" narrative, lead-capture form. No live booking. | Responsive template
E.2 | Villa Room Type design templates (×1) | Standard · Deluxe Lake View · Deluxe Garden View · Suite Lake View · (1 reserve). Design only; build deferred until soft launch. | 1 Figma templates (design-only)
F · SHARED PAGES
F.1 | About Us — brand story | Master-brand origin, founding philosophy, leadership. | Template
F.2 | Experiences (unified) | Wellness · Golf lifestyle · Healing — three editorial pillars shared across properties. | Template + CMS taxonomy
F.3 | Offers & Packages | Filterable by property and audience; experience-led naming (no discount-only). | Template + filtering UI
F.4 | Blog / News — list | CMS-driven, 3-pillar taxonomy, infinite-scroll or pagination. | Template
F.5 | Blog / News — article | SEO-optimised, social-share, related cross-sells to properties & offers. | Template
F.6 | Careers | Open positions list, structured-data JobPosting, application form. | Template
F.7 | Contact | Property-routed forms, map, hotline, Zalo/Messenger, contact-by-purpose. | Template + 3 forms
F.8 | Search | Site-wide search across properties, offers, blog. Suggestion + filter. | Search module + index
F.9 | Information pages | Privacy policy, Terms, Cookie policy, 404, FAQ. | 5 templates
G · BOOKING INTEGRATIONS
G.1 | Golf → VNPay | Tee-time selection · greens-fee calc · VNPay payment · email confirmation · PMS push (data spec to be confirmed by VNPay). | End-to-end booking flow live
G.2 | Swiss-Belresort → Hotel Link → Smile PMS | Real-time availability & rate from Hotel Link channel manager; Smile PMS reservation push; booking confirmation; restorable PMS direct connection. | End-to-end booking flow live
G.3 | Persistent booking widget | Sticky top-right CTA contextual per property ("Book Tee Time" / "Book Room"). Survives scroll. | Sticky widget across all pages
G.4 | Villa lead capture | Newsletter form + interest form for villa launch waitlist; pushed to CRM/CSV export. | Lead capture + 3rd-party feed
H · MULTI-LANGUAGE (VI / EN / KO)
H.1 | Translation framework | Per-language URL structure (/vi /en /ko), language switcher, fallback rules, hreflang tags, locale-aware date/currency. | Multi-language infrastructure
H.2 | Swiss-Bel identity priority for EN/KO | Co-branded header on EN/KO surfaces "Swiss-Belresort Tuyen Lam" prominently for inbound brand recognition. | Conditional branding rules
H.3 | Translation memory hand-off | Translation export/import workflow (XLIFF or CSV) for SAM's translation vendor. Vendor work-out-of-scope. | Translation tooling docs
I · CONTENT MANAGEMENT SYSTEM
I.1 | Headless / hybrid CMS setup | Property pages set to static (admin-only); marketing-managed content (Offers, Blog, News, banners, pop-ups, gallery) freely editable. | CMS instance + admin roles
I.2 | Role-based access control | Roles: Super-admin, Property Editor, Marketing, Translator, Read-only. Audit log. | RBAC + audit
I.3 | Featured Offers Cards engine | Schedule offers, target by property/audience, A/B variant slots, expiry control. | Offers module
I.4 | Pop-up Campaign engine | Large center modal + small left slide-in; schedule, target by URL/segment, frequency capping, dismiss persistence. | Pop-up module
I.5 | Newsletter integration | Form capture → Mailchimp / SendGrid / Klaviyo (one provider). Double opt-in. (Email vendor account by client.) | Newsletter integration live
J · SEO & ANALYTICS
J.1 | Technical SEO baseline | Clean URLs · canonical · meta/OG · Open Graph images · sitemap.xml · robots.txt · hreflang · breadcrumb schema. | SEO audit report (green)
J.2 | Schema markup (Hotel, Golf, Restaurant, Event) | Structured data per property type for richer SERP snippets. | Schema validation pass
J.3 | Google Analytics 4 + GTM | GA4 property, GTM container, event taxonomy, booking-funnel events, source/medium taxonomy. | GA4 + GTM live, events firing
J.4 | Heatmap & session replay | Hotjar or Microsoft Clarity tag on key templates; sample size guidance. | Tag live · sample dashboard
J.5 | 301 redirect map | Full URL-by-URL map from 4 legacy domains to new URLs; bulk redirect rules; 404 catch & monitoring. | 301 map + 404 monitor (90 days)
K · PERFORMANCE, ACCESSIBILITY & TRUST
K.1 | Core Web Vitals optimisation | LCP/INP/CLS green on mobile & desktop for top 10 templates. AVIF/WebP image pipeline. Lazy-load. Critical CSS. | Lighthouse ≥ 90 mobile/desktop
K.2 | WCAG 2.1 AA accessibility | Colour contrast, focus state, keyboard nav, ARIA roles for nav/modals/carousels, alt text framework. | Accessibility audit pass
K.3 | Trust signal layer | Award badges (Swiss-Bel certifications, golf awards), review aggregator widget, partner logos. | Trust components in CMS
K.4 | Browser & device support matrix | Modern evergreen browsers (Chrome, Edge, Safari, Firefox latest-2); iOS 15+; Android 10+; IE not supported. | Documented support matrix
L · SECURITY & COMPLIANCE
L.1 | Security hardening (OWASP Top 10) | Input validation, output encoding, CSRF, secure session, security headers, dependency scanning. Closes posture issues from prior incident. | OWASP checklist signed off
L.2 | Web Application Firewall + DDoS | Cloudflare WAF or equivalent, rate-limit rules, bot mitigation. | WAF rules live
L.3 | Privacy & cookie compliance | Cookie consent banner (Vietnam PDPL + GDPR-aware EU/KR), preference center, privacy policy templates VI/EN/KO. | Cookie consent live + policy
L.4 | Backup & disaster recovery | Daily automated backups, weekly off-site, documented RTO/RPO (4h / 24h), restore tested. | Backup runbook + restore drill
L.5 | Legacy site archive | Static archive of 4 legacy sites + media (read-only) for compliance/historical reference before redirect cutover. | Cold-storage archive bundle
M · 360° VR INTEGRATION
M.1 | VR media re-integration | Existing samtuyenlam.com.vn 360° media re-mounted as tab/modules inside Room Type pages, Property Galleries, and Experience pages. No standalone VR site. | VR module embedded in 4+ pages
N · LIVE CHAT
N.1 | Zalo OA + Facebook Messenger | Persistent floating widget across all pages; conversation routing per property. | Live chat widget live
O · DOMAIN MIGRATION
O.1 | Domain cutover plan | DNS swap, SSL provisioning, redirect deployment, search-console reverification across 4 legacy domains. 90-day monitoring of 404s & rankings. | Cutover runbook executed
P · QA, UAT & LAUNCH
P.1 | Cross-browser & device QA | Test matrix: 5 browsers × 3 device classes × 3 languages = 45 surfaces. | QA report (zero P1/P2 open)
P.2 | Booking-flow end-to-end test | 3 booking systems × 3 user scenarios each = 9 happy-path + 6 edge-case scenarios. | Booking QA sign-off
P.3 | UAT support | Two structured UAT cycles with client team; bug triage; defect resolution. | UAT sign-off
P.4 | Go-live & launch monitoring | Coordinated go-live, real-time monitoring, rollback plan ready. | Successful launch
Q · TRAINING & KNOWLEDGE TRANSFER
Q.1 | CMS training workshops | Two half-day sessions for marketing team: content publishing, offers/pop-ups, blog, media library. | Trained team + recordings
Q.2 | Admin & operations handbook | Written guides: CMS, deployment, backup/restore, escalation paths. | Operations handbook (PDF)
Q.3 | Source code & asset handover | Git repository transfer, design files, infrastructure-as-code, credential vault hand-off. | Repository + key handover
R · POST-LAUNCH HYPERCARE
R.1 | 4-week intensive hypercare | Dedicated team on stand-by post-launch: bug triage <4h response, daily health checks, weekly status call. | Stability sign-off after week 4

## 4. Pricing — Build
BLUE CORAL ▍ Powered by ADNS · 8/7D Phan Huy Ich, Tan Binh, Ho Chi Minh City · +84 979 477 101 · hello@bluecoral.vn
Phase 1 — Design, Build & Launch — Detailed Pricing
Blended rate: 19.25 USD / hour · FX reference: 1 USD = 26,000 VND · Hour cost: 500,500 VND/h · All figures incl. 10% VAT in Grand Total
WORKSTREAM | DELIVERABLE | EFFORT (HOURS) |  |  |  |  | PRICE (VND) | PRICE (USD) | QTY | NOTES
|  | BA | DESIGN | DEV | PM | TOTAL
A. Discovery & Foundation | Information architecture & sitemap | 12 | 8 |  | 4 | 24 | 12012000 | 462 | 1 | Sitemap, URL strategy, hreflang map.
| Design system & component library |  | 60 | 16 | 8 | 84 | 42042000 | 1617 | 1 | Figma system: typography, colour, components, dark/light tokens.
B. Brand Home | Brand Home — master template (10 blocks) | 8 | 56 | 48 | 6 | 118 | 59059000 | 2271.5 | 1 | Hero video, brand narrative, 3 gateways, 3 pillars, offers, audience links, gallery, blog, newsletter, footer.
C. Golf Property | Golf property overview (6 blocks) | 6 | 32 | 28 | 4 | 70 | 35035000 | 1347.5 | 1 | Hero · Course intro · 18-Hole/Coaching/Club House · Lifestyle · Gallery + 360° · CTA.
| Club House sub-pages (Restaurant · Rooms · Pro Shop) | 2 | 18 | 16 | 3 | 39 | 58558500 | 2252.25 | 3 | 3 sub-templates.
D. Swiss-Belresort | Resort property overview (7 blocks) | 8 | 40 | 32 | 6 | 86 | 43043000 | 1655.5 | 1 | Hero w/ Swiss-Bel identity · 151-room intro · Room grid · Spa · Dining · MICE · Experiences · Gallery · CTA.
| Room Type detail pages | 3 | 24 | 18 | 3 | 48 | 72072000 | 2772 | 3 | 3 room layouts: Deluxe MV/GV, Studio MV, Family Deluxe, King Suite, Royal Suite, Standard.
| Spa & Wellness sub-page | 2 | 16 | 12 | 2 | 32 | 16016000 | 616 | 1 | Curated wellness journeys, not service list.
| Dining sub-page | 2 | 12 | 10 | 2 | 26 | 13013000 | 500.5 | 1 | Restaurant & bar storytelling, menu module.
| MICE & Events sub-page | 3 | 16 | 14 | 3 | 36 | 18018000 | 693 | 1 | Venue specs, capacity, RFP form.
E. Villa (deferred launch) | Villa teaser (Coming Soon) + lead form | 4 | 24 | 12 | 2 | 42 | 21021000 | 808.5 | 1 | No live booking. Brand storytelling + waitlist capture.
| Villa Room Type design templates (design-only) | 2 | 32 |  | 4 | 38 | 57057000 | 2194.5 | 3 | Standard, Deluxe Lake/Garden View, Suite Lake View, +1. Build deferred.
F. Shared Pages | About Us — brand story | 4 | 16 | 12 | 2 | 34 | 17017000 | 654.5 | 1
| Experiences (Wellness · Golf · Healing) | 4 | 20 | 18 | 2 | 44 | 22022000 | 847 | 1 | 3 editorial pillars shared across properties.
| Offers & Packages — filterable | 4 | 20 | 22 | 2 | 48 | 24024000 | 924 | 1 | Filter by property × audience; CMS-driven cards.
| Blog / News — listing | 2 | 14 | 18 | 2 | 36 | 18018000 | 693 | 1
| Blog / News — article detail | 2 | 12 | 12 | 2 | 28 | 14014000 | 539 | 1
| Careers (with JobPosting schema) | 2 | 12 | 14 | 2 | 30 | 15015000 | 577.5 | 1
| Contact — property-routed forms (×3) | 2 | 14 | 18 | 2 | 36 | 18018000 | 693 | 1 | Map, hotline, Zalo/Messenger embed.
| Search — site-wide | 2 | 10 | 22 | 2 | 36 | 18018000 | 693 | 1 | Cross-property search index.
| Information pages (Privacy/Terms/Cookie/404/FAQ) |  | 8 | 8 | 1 | 17 | — | — | One-time | 5 templates · mostly text.
G. Booking Integrations | Golf → VNPay payment flow | 6 |  | 32 | 4 | 42 | 21021000 | 808.5 | 1 | Tee-time, fee calc, VNPay, confirmation, PMS push.
| Swiss-Belresort → Hotel Link → Smile PMS | 8 |  | 40 | 6 | 54 | 27027000 | 1039.5 | 1 | Real-time avail/rate, reservation push, confirmation.
| Persistent booking widget (sticky) | 2 | 6 | 12 | 2 | 22 | 11011000 | 423.5 | 1 | Top-right sticky CTA contextual per property.
| Villa lead capture → CRM/CSV | 2 |  | 10 | 2 | 14 | 7007000 | 269.5 | 1 | Form + webhook to client CRM.
H. Multi-language | Multi-language framework (VI/EN/KO) | 4 | 8 | 36 | 4 | 52 | 26026000 | 1001 | 1 | URL structure, switcher, hreflang, locale-aware formatting.
I. CMS | CMS setup (headless/hybrid) + DB structure | 12 |  | 28 | 6 | 46 | — | — | 1 | Multi-property data model, multi-language entries, media library.
| Role-based access control + audit log | 8 |  | 12 | 2 | 22 | 11011000 | 423.5 | 1 | Super-admin, Property Editor, Marketing, Translator, Read-only.
| Featured Offers Cards engine | 4 | 8 | 18 | 2 | 32 | 16016000 | 616 | 1 | Schedule, target, A/B variants, expiry.
| Pop-up Campaign engine | 4 | 8 | 22 | 2 | 36 | 18018000 | 693 | 1 | Large center modal + small left slide-in; schedule, target, frequency cap.
| Newsletter integration (one provider) | 2 | 4 | 12 | 2 | 20 | 10010000 | 385 | 1 | Mailchimp/SendGrid/Klaviyo. Vendor account by client.
| Content & media migration plan | 8 |  | 12 | 2 | 22 | — | — | One-time | Mapping from 4 legacy sites; asset re-encoding.
J. SEO & Analytics | Technical SEO baseline | 4 |  | 20 | 2 | 26 | 13013000 | 500.5 | 1 | Canonical, meta/OG, sitemap.xml, robots.txt, breadcrumb schema, hreflang.
| Schema markup (Hotel · Golf · Restaurant · Event) | 2 |  | 14 | 2 | 18 | 9009000 | 346.5 | 1 | Structured data for rich SERP snippets.
| GA4 + GTM event taxonomy | 3 |  | 14 | 2 | 19 | 9509500 | 365.75 | 1 | Booking-funnel events, source/medium, custom dimensions.
| Heatmap & session replay (Hotjar/Clarity) | 1 |  | 6 | 1 | 8 | 4004000 | 154 | 1
| 301 redirect map (URL-by-URL) | 8 |  | 16 | 4 | 28 | 14014000 | 539 | 1 | Map across 4 legacy domains + bulk rules.
K. Performance & A11y | Core Web Vitals optimisation | 2 | 4 | 24 | 3 | 33 | 16516500 | 635.25 | 1 | LCP/INP/CLS green; AVIF/WebP pipeline; critical CSS.
| WCAG 2.1 AA accessibility | 4 | 6 | 18 | 3 | 31 | 15515500 | 596.75 | 1 | Contrast, focus, keyboard nav, ARIA, alt-text framework.
| Trust signal layer (awards · Swiss-Bel · reviews) | 2 | 8 | 12 | 2 | 24 | 12012000 | 462 | 1 | CMS-managed badges & review aggregator widget.
L. Security & Compliance | Security hardening (OWASP Top 10) | 3 |  | 18 | 3 | 24 | 12012000 | 462 | 1 | Closes posture issues from prior incident.
| WAF + DDoS protection configuration | 1 |  | 8 | 2 | 11 | 5505500 | 211.75 | 1
| Cookie consent + privacy policy (VI/EN/KO) | 3 | 4 | 14 | 2 | 23 | 11511500 | 442.75 | 1 | Vietnam PDPL + GDPR-aware preference center.
| Backup & DR runbook + restore drill | 2 |  | 10 | 2 | 14 | — | — | One-time | RTO 4h / RPO 24h; restore drill before go-live.
| Legacy site archive (4 domains, read-only) | 2 |  | 12 | 2 | 16 | — | — | One-time | Static snapshot + media bundle for compliance.
M. 360° VR | 360° VR re-integration into property pages | 6 |  | 36 | 6 | 48 | 24024000 | 924 | 1 | Embed existing media as tabs/modules in Room Type + Gallery + Experiences.
N. Live Chat | Zalo OA + Facebook Messenger widget | 2 | 4 | 5 | 2 | 13 | 6506500 | 250.25 | 1
O. Migration | Domain cutover plan + 90-day 404 monitor | 4 |  | 20 | 6 | 30 | 15015000 | 577.5 | 1 | DNS, SSL, redirect deploy, search-console reverification.
P. QA & Launch | Cross-browser & device QA | 8 |  | 28 | 4 | 40 | 20020000 | 770 | 1 | 5 browsers × 3 device classes × 3 languages.
| UAT support (2 cycles) | 8 |  | 16 | 6 | 30 | — | — | 1
| Go-live & launch monitoring | 2 |  | 12 | 4 | 18 | — | — | One-time | Coordinated go-live; rollback plan ready.
Q. Training & Handover | CMS training workshops (×2 half-day) | 4 |  | 6 | 4 | 14 | 7007000 | 269.5 | 1 | Recorded sessions for marketing team.
| Admin & operations handbook | 8 | 4 | 4 | 2 | 18 | — | — | One-time | PDF + searchable web doc.
| Source code + asset handover | 2 |  | 6 | 2 | 10 | — | — | One-time | Git transfer, infra-as-code, credential vault.
SUBTOTAL (before discount & VAT) | [6 empty] | 935434500 | 35978.25
Volume discount (10%) | [6 empty] | -93543450 | -3597.825
VAT (10%) | [6 empty] | / | #VALUE!
GRAND TOTAL (VAT included) | [6 empty] | 841891050 | 32380.425
Effort estimates apply our blended team rate (Business Analysis, Visual Design, Engineering, Project Management). One-time items are fixed-fee. Volume discount of 15% reflects programme scale across three properties. Grand Total is VAT-inclusive.

## 5. Pricing — Hosting
BLUE CORAL ▍ Powered by ADNS · 8/7D Phan Huy Ich, Tan Binh, Ho Chi Minh City · +84 979 477 101 · hello@bluecoral.vn
Phase 2 — Hosting & Managed Services (Year 1)
Year-1 infrastructure and SLA-backed managed services. Hosted on enterprise cloud with daily backups, hardened security posture (post-incident baseline), and 20 hours of dedicated technical support per month.
WORKSTREAM | ITEM | PRICE (VND) | TERM | DESCRIPTION
Cloud Infrastructure | Enterprise hosting — multi-site, high-traffic profile | 28800000 | 12 Months | CPU 4 cores · RAM 8 GB · SSD 120 GB · daily backup · weekly snapshot
| CDN — Cloudflare Pro (global edge, image optimisation) | 7200000 | 12 Months | Tunes Core Web Vitals; AVIF/WebP; global cache; bot management
| SSL Wildcard certificate (all subdomains) | 0 | 12 Months | Valued at 1,800,000 ₫ — included at no charge
| WAF + DDoS protection (application layer) | 0 | 12 Months | Valued at 5,580,000 ₫ — included at no charge. Mandatory given prior incident posture.
Managed Services | 5 hours of technical support per month · Managed hosting & SSL · Daily backups + weekly off-site · Security & threat scans (weekly) · Uptime monitoring 99.9% SLA · Performance & SEO on-page tweaks · Priority response < 4 hours · Module configuration & consulting · Source-code & version control · Monthly performance report | 26400000 | 12 Months | 3 months free at start — valued 6,600,000 ₫
Setup | Initial migration & DNS cutover | Free of charge | — | DNS swap from legacy hosts; SSL provisioning; first-deploy.
SUBTOTAL (before discount & VAT) |  | 62400000
VAT (10%) |  | 3600000
GRAND TOTAL — Phase 2 (VAT included) |  | 66000000
Billing options — quarterly (default) or annual prepayment (additional 5% discount). Service term renewable annually. Third-party license fees (Hotel Link, VNPay, Hotjar, Zalo OA) are billed directly by the providers and are not included in this Phase 2 figure.

## 6. Timeline
BLUE CORAL ▍ Powered by ADNS · 8/7D Phan Huy Ich, Tan Binh, Ho Chi Minh City · +84 979 477 101 · hello@bluecoral.vn
Project Timeline — 20-Week Build + 12-Month Operations
WORKSTREAM | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | KEY DELIVERABLE
Phase | W1: M0 · Discovery; W3: M1 · Design; W9: M2 · Build; W15: M3 · Integrate; W19: M4 · Launch
Discovery workshops | [20 empty] | Discovery report + asset audit | bar: W1 to W2
Information architecture | [20 empty] | Sitemap & URL strategy approved | bar: W1 to W3
Brand narrative | [20 empty] | Brand voice + content strategy | bar: W2 to W4
Design system | [20 empty] | Design system in Figma | bar: W3 to W6
Visual design — templates | [20 empty] | 14 templates approved | bar: W4 to W8
Backend & CMS setup | [20 empty] | CMS + RBAC operational | bar: W7 to W12
Frontend build | [20 empty] | Static build delivered | bar: W8 to W14
Multi-language framework | [20 empty] | VI/EN/KO switching live | bar: W10 to W13
Golf booking → VNPay | [20 empty] | Booking flow live | bar: W13 to W16
Resort booking → Hotel Link | [20 empty] | Booking flow live | bar: W13 to W17
360° VR integration | [20 empty] | 360° embedded in pages | bar: W14 to W17
Live chat · Analytics · SEO | [20 empty] | GA4 + chat + SEO baseline | bar: W15 to W18
Content & media migration | [20 empty] | Content live in CMS | bar: W12 to W18
QA — cross-browser & device | [20 empty] | QA report (P1/P2 zero) | bar: W17 to W19
UAT — 2 client cycles | [20 empty] | UAT sign-off | bar: W18 to W19
301 redirects + cutover | [20 empty] | 4 legacy domains redirected | bar: W19 to W20
Security hardening | [20 empty] | OWASP checklist signed off | bar: W18 to W20
Go-live + monitoring | [20 empty] | Production launch | bar: W20
Training & handover | [20 empty] | Trained team + handbook | bar: W19 to W20
POST-LAUNCH — 4 weeks intensive hypercare (W21-W24) · then 12 months Managed Services with SLA & monthly performance reviews
Legend: | W2: Discovery; W5: Design / Build; W8: Integration; W11: Launch

## 7. Commercial Terms
BLUE CORAL ▍ Powered by ADNS · 8/7D Phan Huy Ich, Tan Binh, Ho Chi Minh City · +84 979 477 101 · hello@bluecoral.vn
Commercial Terms, Assumptions & Exclusions
01 · PAYMENT SCHEDULE — PHASE 1
Milestone 1 — Kickoff | 30% · Payable within 7 business days of contract signature.
Milestone 2 — Design Approval | 30% · Payable upon written acceptance of UI/UX visual design (end of M1).
Milestone 3 — UAT Sign-off | 30% · Payable upon UAT acceptance, prior to production launch (end of M3).
Milestone 4 — Launch & Handover | 10% · Payable within 14 business days of go-live and complete handover (end of M4).
Phase 2 — Hosting & Support | Quarterly billing in advance, OR annual prepayment with 5% additional discount.
02 · CHANGE REQUEST POLICY
Minor changes | Changes inside agreed scope (e.g. copy tweaks, image swaps, layout micro-adjustments within a delivered template) are handled at no additional charge during the active sprint.
Scope changes | Net-new pages, integrations, templates, or workflows are estimated separately and signed off as a Change Order before work begins. Billed at the blended rate.
Design revisions | Three rounds of design revisions are included per template. Additional rounds quoted at the blended rate.
Scope freeze | Scope and visual design are frozen at end of M1. Subsequent changes follow the Change Order process.
03 · WARRANTY & SUPPORT
Post-launch warranty (90 days) | Defects against agreed acceptance criteria fixed at no additional charge for 90 days from go-live.
Hypercare (4 weeks) | Dedicated team on standby immediately post-launch: <4-hour response on production incidents, daily health checks, weekly status call.
Managed services (Phase 2) | 20 hours of monthly support, priority response <4 hours, with full SLA defined in the Hosting & Managed Services schedule.
04 · ENGAGEMENT ASSUMPTIONS
✓ | Client provides a single empowered decision-maker per workstream (Marketing, IT, Property GMs).
✓ | Client provides master content in Vietnamese on agreed schedule. Each week of content delay extends launch by the equivalent duration.
✓ | Client provides API credentials and signs vendor NDAs/agreements with VNPay, Hotel Link, Smile PMS, Zalo OA, Facebook in time for M3 integration.
✓ | Client provides existing photo & video assets (current 360° media, brand photography, room photography) by end of M0.
✓ | EN and KO translations are produced by Client's translation vendor using our XLIFF/CSV export. Translation execution is out-of-scope.
✓ | Client appoints UAT testers for two structured cycles in M4.
✓ | Hosting Phase 2 begins on go-live; first invoice issued within 7 days of launch.
✓ | All pricing is in Vietnamese Dong (VND). USD figures are reference only at the FX rate stated.
05 · OUT OF SCOPE / EXCLUSIONS
✗ | Third-party SaaS license fees (Hotel Link, VNPay merchant fees, Hotjar, Zalo OA premium, Mailchimp, font/stock asset licenses) — billed directly by providers.
✗ | New filming, photography, drone capture, or 3D scans (for hero video and new room photography). Quoted separately if required.
✗ | Content writing in Vietnamese (master content) and translation production into EN and KO.
✗ | Ongoing SEO content marketing, paid media management, social media management — quoted as separate engagement.
✗ | Property Management System (PMS) software licensing and configuration changes inside Smile PMS.
✗ | Hardware procurement (servers, devices) and on-premise infrastructure changes.
✗ | Custom mobile apps (iOS/Android). The website is fully responsive on mobile browsers.
✗ | Loyalty programme platform, gift voucher engine, or third-party CRM integration beyond the Newsletter and Lead-capture handoff specified.
✗ | Re-design or feature work after the 90-day warranty period — handled under Phase 2 Managed Services time pool or as a separate Change Order.
06 · INTELLECTUAL PROPERTY & CONFIDENTIALITY
Custom code & design | Upon final payment, all custom code and original design assets created specifically for SAM Tuyen Lam become the exclusive property of the Client.
Third-party components | Open-source libraries and third-party plug-ins remain under their original licenses (MIT, Apache 2.0, etc.). License compliance documentation provided at handover.
Confidentiality | Both parties agree to keep this proposal, the engagement, and all shared business information confidential for a period of 3 years from disclosure.
Portfolio rights | Blue Coral may reference the project in our portfolio (name, screenshots, public-facing case study) unless Client opts out in writing.
07 · ACCEPTANCE
By signing below, both parties accept the scope, pricing, timeline, and commercial terms set out in this proposal and its referenced sheets.
FOR BLUE CORAL (ADNS)
Name: | Mr. Nguyen
Title: | Managing Director
Signature:
Date:
FOR SAM TUYEN LAM
Name: | ______________
Title: | Authorised Representative
Signature:
Date: