COMMUNICATION PLAN

Databricks-P1 — Blue Coral (BC) ↔ VinaCapital (VC)

# 1. Mục đích

Communication Plan cho dự án Databricks-P1 quy định AI cần biết CÁI GÌ, KHI NÀO, qua KÊNH NÀO, và AI chịu trách nhiệm. Vì dự án có 3 workstream chạy song song từ 18/05/2026 đến 09/07/2026 (~7.5 tuần), comm phải đủ chặt để tránh dependency lock nhưng đủ thoáng để không tiêu thời gian thực thi.

# 2. Stakeholder Matrix

| Stakeholder | Name | Interest | Influence | Strategy |
| --- | --- | --- | --- | --- |
| VC Project Owner | Khiem Pham | High | High | Manage Closely — daily contact, weekly status, bi-weekly Steerco |
| VC Tech Lead | Hien Vo | High | High | Manage Closely — WS3 daily, architecture review |
| VC SME (per system) | Per system (9 system) | High | Medium | Keep Engaged — assessment workshop WS1/WS2 |
| VC Security / Compliance | TBD (nominate at Kickoff) | Medium | High | Manage Closely — checkpoint WS3 Design |
| VC IT Infra | TBD (nominate at Kickoff) | Medium | Medium | Keep Informed — provisioning, access |
| BC CEO / PO | Nguyen Le | High | High | Manage Closely — Steerco, escalation |
| BC PM | Tin Huynh | High | High | Owner of plan — drive all comm |
| BC Tech Lead / Architect | Dung Phan | High | High | Daily WS3 + architecture decisions |
| BC Finance BA | Tess Pham | High | Medium | Workshop WS1/WS2 cho Finance system (PMS, ESM, Custodian, VSDC); requirement analysis |
| BC WS1 Lead | TBD | High | Medium | Daily WS1, weekly status |
| BC WS2 Lead | TBD | High | Medium | Daily WS2, weekly status |

Note: tên cụ thể của WS1/WS2 Lead, Security, Infra contact sẽ được fill in tại Kickoff Meeting (19/05/2026) và cập nhật vào Stakeholder Register tại /01_Governance/Stakeholder_Register.xlsx.

# 3. Communication Matrix

| Loại comm | Audience | Kênh | Tần suất | Owner |
| --- | --- | --- | --- | --- |
| Daily Sync 3 WS | Tin Huynh + 3 WS Lead + Hien Vo (opt) | Teams Meeting | Daily 09:00 (15–20') | Tin Huynh |
| Daily summary | Core team | Teams post #daily-sync | Daily EOD | WS Lead per WS |
| WS1 Assessment Workshop | WS1 Lead + VC SME PMS/MarketS | Teams + onsite | On-demand per system | WS1 Lead |
| WS2 Assessment Workshop | WS2 Lead + VC SME source system | Teams + onsite | On-demand per system | WS2 Lead |
| Architecture Review (WS3) | Dung Phan + Hien Vo | Teams + Lucid/Drawio | Per design milestone | Dung Phan |
| Weekly Status Meeting | Tin Huynh + Khiem Pham (+ Hien Vo) | Teams Meeting (recorded) | Weekly T6 16:00 (45') | Tin Huynh |
| Weekly Status Report | DL-Project-Extended | Email + SharePoint /07_Reports | Weekly T6 EOD | Tin Huynh |
| Steering Committee | Nguyen Le + Khiem Pham + Tin Huynh | Teams Meeting (recorded) | Bi-weekly (45') | Tin Huynh |
| WS Milestone Review | WS Lead + Khiem Pham + Tin Huynh | Teams Meeting (recorded) | Per milestone | WS Lead |
| Change Request | Tin Huynh ↔ Khiem Pham (+ Nguyen Le nếu >5%) | Email + SharePoint CR form | On-demand | CR initiator |
| Incident / Escalation | Tin Huynh + Khiem Pham (+ Sponsor) | Phone/Teams call + email | Real-time | Person phát hiện |
| PoC Demo | Full team + Khiem Pham + VC stakeholders | Teams Meeting (recorded) | 29/06 – 03/07/2026 | Dung Phan |
| Closure Meeting | Full team + Sponsors | Teams Meeting + onsite | 06/07 – 10/07/2026 | Tin Huynh |
| Retrospective | BC team (VC optional) | Teams Meeting | Per milestone + final | Tin Huynh |

# 4. Cadence Calendar (week typical)

| Day | Time (GMT+7) | Event | Channel |
| --- | --- | --- | --- |
| Mon | 09:00 | Daily Sync 3 WS | Teams call |
| Mon–Fri | 09:00 | Daily Sync 3 WS | Teams call |
| Mon–Fri | EOD | Daily Summary post per WS | Teams #daily-sync |
| Tue/Thu | On-demand | WS1/WS2 Assessment Workshop với SME | Teams + onsite |
| Wed | On-demand | Architecture Review (WS3) | Teams + Lucid |
| Fri | 16:00 | Weekly Status Meeting | Teams call (recorded) |
| Fri | EOD | Weekly Status Report sent | Email + SharePoint /07_Reports |
| Bi-weekly (T4) | 14:00 | Steering Committee | Teams call (recorded) |
| Per milestone | — | WS Milestone Review | Teams call (recorded) |

Working hours: 09:00–18:00 GMT+7 (T2–T6). Working mode: Hybrid (onsite VinaCapital office + remote). Onsite days tại VC office sẽ được thống nhất tại Kickoff Meeting.

# 5. Status Report Template

Mỗi Weekly Status Report (max 2 trang) bao gồm:

Overall RAG (Schedule / Scope / Risk) per workstream — màu Red / Amber / Green

Workstream progress: WS1 / WS2 / WS3 / WS4 — % complete + milestone status

Highlights tuần (top 3–5 thành tựu)

Lowlights / Issues (top 3 vấn đề + owner + action)

Schedule view: milestone tới (M1–M7) + ngày dự kiến

Burn-down effort per WS

Top 5 risks + mitigation status

Decisions needed (từ VC side)

Look-ahead: ưu tiên tuần tới per WS

# 6. Escalation Path & SLA

| Severity | Định nghĩa | Escalate đến | SLA phản hồi |
| --- | --- | --- | --- |
| Sev1 — Critical | Access blocker, security incident, milestone tại risk | Tin Huynh + Khiem Pham + Nguyen Le | 30' (giờ làm việc) / 1h (ngoài giờ) |
| Sev2 — High | Workstream blocker, no workaround | Tin Huynh + Hien Vo | 2h |
| Sev3 — Medium | Task blocker, có workaround | Tin Huynh + Khiem Pham | 1 business day |
| Sev4 — Low | Cosmetic, request enhancement | DevOps ticket → Tin Huynh review | 3 business days |

## 6.1 Escalation Levels

L1: Team member → WS Lead / Dung Phan

L2: WS Lead / Dung Phan → Tin Huynh

L3: Tin Huynh → Khiem Pham (BC side) hoặc Nguyen Le (escalation BC)

L4: Nguyen Le + Khiem Pham → Steerco / Executive (Sev1 escalate ngay)

# 7. Tools & Templates

| Mục đích | Tool / Template | Vị trí |
| --- | --- | --- |
| Weekly status template | .docx | SharePoint /01_Governance/_Templates/ |
| Steerco deck template | .pptx | SharePoint /01_Governance/_Templates/ |
| Workshop note template (WS1/WS2) | .docx | SharePoint /01_Governance/_Templates/ |
| Meeting minutes template | .docx | SharePoint /01_Governance/_Templates/ |
| CR form | .docx | SharePoint /01_Governance/_Templates/ |
| ADR template | .md / .docx | SharePoint /01_Governance/_Templates/ |
| Decision log | .xlsx | SharePoint /01_Governance/RAID_Log.xlsx |
| RAID log | .xlsx | SharePoint /01_Governance/RAID_Log.xlsx |
| Project Teams channel | Teams group | Tenant VinaCapital |

# 8. Distribution Lists / Teams Channels

| Group / Channel | Members | Khi nào dùng |
| --- | --- | --- |
| Teams #general | Toàn bộ project team | Announcement, pinned doc |
| Teams #daily-sync | Core team | Daily standup + EOD summary |
| Teams #ws1-assessment-pms | WS1 Lead + relevant SME | WS1 discussion |
| Teams #ws2-assessment-sources | WS2 Lead + relevant SME | WS2 discussion |
| Teams #ws3-core-platform | Dung Phan + Hien Vo + devs | WS3 technical discussion |
| Teams #governance | Tin Huynh + Khiem Pham + sponsors | Steerco material, formal announcement |
| DL-VC-BC-Core | Tin Huynh, Dung Phan, Khiem Pham, Hien Vo | Day-to-day email |
| DL-VC-BC-Steerco | Nguyen Le, Khiem Pham, Tin Huynh | Steerco invite, escalation email |
| DL-VC-BC-Extended | Core + SME + WS Leads | Weekly status email distribution |

# 9. Anti-Patterns (cần tránh)

Gửi cùng nội dung qua nhiều kênh (email + Teams + DM) → noise + không rõ kênh of-record

Quyết định scope/design chỉ trong DM hoặc voice call không note → không truy được

BCC sponsor mỗi email → mất niềm tin, sponsor bị noise

Status report quá dài (> 3 trang) → không ai đọc → đổi thành dashboard

Họp không có agenda + không có minutes

Sử dụng emoji/icon mơ hồ thay cho RAG status

Báo cáo 'Green' nhưng phía sau có Sev2 chưa giải quyết → mất uy tín

# 10. Review

Communication Plan được review sau tuần 2 (18/05/2026 + 14 ngày) và tại mỗi milestone review. Vì timeline ngắn, điều chỉnh nhanh nếu cadence không phù hợp. Phiên bản mới ghi đè tại SharePoint /01_Governance/Communication_Plan/.

# Sign-off

Các bên xác nhận đã đọc, hiểu và đồng ý với nội dung tài liệu này.

| Khiem Pham (VC — Project Owner) | Tin Huynh (BC — PM) |
| --- | --- |
| Họ tên: ________________________ | Họ tên: ________________________ |
| Chức vụ: ________________________ | Chức vụ: ________________________ |
| Ngày ký: ________________________ | Ngày ký: ________________________ |